## Marketing Plan Data
Marketing Plan Data
STATUS COLOR LEGEND & TOGGLE
|  | Not Started | In Progress | Delayed | Complete | Custom 1 | Custom 2 | Custom 3 | Custom 4
|  | ON | ON | OFF | ON | OFF | OFF | OFF | OFF
|  |  |  | ANTICIPATED |  | ACTUAL |  | COST
TASK | STATUS | OWNER | ASSIGNED TO | START DATE | END DATE | START DATE | END DATE | ESTIMATED | ACTUAL
Product Analysis | In Progress | John C. | John C. | 2012-07-01 | 2012-08-01 | 2012-06-28 |  | 1500 | 1250
Design Storyboards | In Progress | Mark M. | John C. | 2012-07-15 | 2012-08-15 | 2012-07-13 |  | 2000 | 1840
Review Storyboard Design | Complete | Mark M. | John C. | 2012-08-01 | 2012-08-20 |  |  | 1450
Research Analysis Phase I | Delayed | Kamil A. | Andrew L. | 2012-06-01 | 2012-07-01 | 2012-06-01 | 2012-06-28 | 3000 | 3200
Advertising Content Creation Phase I | Delayed | Kamil A. | Timothy S. | 2012-09-01 | 2012-09-15 |  |  | 500
Product Requirement Definitions | Delayed | Kamil A. | Vivian A. |  |  |  |  | 575 | 125
Prototype Development Specifications | In Progress | Kamil A. | Gabe F. | 2012-09-12 | 2012-09-25 |  |  | 1750
Quality Control, Progress Reports | In Progress | Mark M. | Kamil A. | 2012-07-01 | 2012-10-01 | 2012-07-01 |  | 925 | 250
Create Storyboards | Not Started | Mark M. | John C. | 2012-07-15 | 2012-08-15 | 2012-07-13 |  | 2000 | 1840
Review Storyboards with Graphic Artists | Delayed | Mark M. | John C. | 2012-08-01 | 2012-08-20 |  |  | 1450
Research Analysis Phase II | Complete | Kamil A. | Andrew L. | 2012-06-01 | 2012-07-01 | 2012-06-01 | 2012-06-28 | 3000 | 3200
Advertising Content Creation Phase II | Not Started | Kamil A. | Timothy S. | 2012-09-01 | 2012-09-15 |  |  | 500
MARKETING PLAN LISTS
Personalize this template! Modify the Status category names in row 6 to match your marketing plan data. Use the ON/OFF values to toggle row highlight for that status.

## List Data
Marketing Plan Lists
NAME | TITLE
John C. | Marketing Specialist
Mark M. | Marketing Manager
Kamil A. | Project Manager
Phil G. | Marketing Analyst
Andrew L. | Research Coordinator
Timothy S. | Marketing Specialist
Vivian A. | Marketing Analyst
Gabe F. | Associate Marketing Manager
MARKETING PLAN DATA