## Risk Assessment Scorecard
[Company Name]
Risk Assessment and Financial Impact Model
[Date]
Gray cells are calculated for you. You do not need to enter anything into them.
Risk area | Potential risk | Number of annual incidents | Cost per incident | Total annual cost | Probability of occurrence | Weighted cost | Mitigating strategies & controls | Annual control cost | Cost/benefit | Decision summary | Owner
Competitive | Contoso, Ltd. might introduce a superior offering on June 30 to compete with our #1 product line. | 1 | 1850000 | 1850000 | 75% | 1387500 | Reduce price by 25% on May 31 to keep the volume stable. | 1150000 | 237500 | Monitor competitor progress and implement new strategy if required. | Kirk DeGrasse
|  |  |  | 0 |  | 0 |  |  | 0
Economic/political |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 |  |  | 0
Regulatory/legal | Need to meet Sarbanes-Oxley 404 (SOX) compliance requirements by target date. | 1 | 15000000 | 15000000 | 5% | 750000 | Establish SOX Compliance Office on January 15 to ensure compliance 30 days before required date. | 1200000 | -450000 | Despite negative cost/benefit, proceed with SOX compliance because of the company's high visibility. | Kim Ralls
|  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 |  |  | 0
Technological | Potential exists for hackers to compromise internal network and obtain confidential customer or employee information. | 5 | 4000000 | 20000000 | 10% | 2000000 | Upgrade firewall to latest version; install proxy server in Q2. | 750000 | 1250000 | Continue to monitor technology to ensure that our company's and our clients' information is protected. Intrusion would have an enormous effect. | Carol Philips
|  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 |  |  | 0
Operational | If a key parts supplier in Eastern Asia suddenly goes out of business, it will risk 25% of production. | 1 | 1250000 | 1250000 | 75% | 937500 | Partner with alternate suppliers to reduce reliance on dominant supplier. | 937500 | 0 | Begin negotiating terms with other key suppliers; take care not to lock into minimum volume agreements. | Michiko Osada
|  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 |  |  | 0
Financial |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 0 |  | 0 |  |  | 0
TOTALS |  |  | 22100000 | 38100000 |  | 5075000 |  | 4037500 | 1037500

## Sample 1—Competitive Risk
Sample—Competitive risk
Scenario: Contoso, Ltd. introduces superior offering in June to compete with our #1 product line.
| Units | Dollars | Annual growth rate
Product X sales—year 1 | 9 | 5000000 | –
Product X sales—year 2 | 10 | 5500000 | 10%
Product X sales—year 3 | 11 | 6000000 | 9.091%
Projected sales—year 4 | 12 | 6545454.5455
First half sales weighting |  | 30%
Second half sales weighting |  | 70%
Second half sales at risk |  | 4581818.1818
Number of units at risk |  | 8.4
Cost per unit |  | 500000
Impact with no mitigation
Sales reduction |  | 40% | Note: based on market surveys
Reduced number of units sold |  | 5.04
Revised second half product sales |  | 2749090.9091
Revenue impact |  | -1832727.2727 | Note: round to $1,850,000 for scorecard
Mitigation through price reduction
Unit price reduction required to maintain volume |  | 25% | Note: based on market surveys
Number of units at risk |  | 8.4
Revised second half product sales |  | 3436363.6364
Revenue impact |  | -1145454.5455 | Note: round to $1,150,000 on scorecard
Mitigation of competitive impact with price reduction |  | 687272.7273

## Sample 2—Operational Risk
Sample—Operational risk
Scenario: Key materials supplier in East Asia goes out of business, risking 25% of production for Product X.
Expected Product X revenues—2004 |  | 5000000
Cost of goods sold
Labor |  | 1000000
Materials |  | 2000000
Other direct costs |  | 500000
Total cost of goods sold |  | 3500000
Gross margin |  | 1500000
Margin contribution percentage |  | 30%
Impact with no mitigation
Reduction in materials availability |  | 25%
Revised product sales |  | 3750000
Revenue impact |  | -1250000
Mitigation through new supplier
Reduction in materials availability |  | 18.75%
Revised product sales |  | 4062500
Revenue impact |  | -937500
Mitigation of impact with other suppliers |  | 312500
Materials breakdown
| % Contribution | Amount
At-risk supplier | 25% | 500000
All other suppliers | 75% | 1500000
Total materials costs |  | 2000000
Ability to mitigate materials loss through other suppliers |  | 25%