## Source Data
<Company Name>
Project Time Performance Tracking
Project Name | Project Type | Estimated Start | Estimated Finish | Estimated Days | Actual Start | Actual Finish | Actual Days | Variance (in Days) | Estimated Hours | Actual Hours | Variance (in Hours)
A. Datum Corporation | Business Continuity Planning | 2004-01-04 | 2004-03-04 | 60 | 2004-01-04 | 2004-03-09 | 65 | 5 | 200 | 220 | 20
Alpine Ski House | Cost Reduction | 2004-01-20 | 2004-02-21 | 31 | 2004-01-25 | 2004-02-20 | 25 | -6 | 400 | 390 | -10
Baldwin Museum of Science | Process Improvement | 2004-02-06 | 2004-04-16 | 70 | 2004-02-10 | 2004-04-23 | 73 | 3 | 500 | 500 | 0
Blue Yonder Airlines | Cost Reduction | 2004-02-24 | 2004-04-25 | 61 | 2004-02-22 | 2004-04-29 | 67 | 6 | 150 | 145 | -5
City Power & Light | Sarbanes-Oxley | 2004-03-08 | 2004-03-18 | 10 | 2004-03-09 | 2004-03-28 | 19 | 9 | 250 | 255 | 5
Coho Vineyard | Strategic Planning | 2004-03-19 | 2004-04-29 | 40 | 2004-03-19 | 2004-05-05 | 46 | 6 | 300 | 310 | 10
Coho Winery | Cost Reduction | 2004-04-10 | 2004-04-20 | 10 | 2004-04-12 | 2004-04-17 | 5 | -5 | 500 | 510 | 10
Coho Vineyard & Winery | Sarbanes-Oxley | 2004-04-18 | 2004-05-12 | 24 | 2004-04-17 | 2004-05-16 | 29 | 5 | 750 | 790 | 40
Contoso, Ltd. | Cost Reduction | 2004-05-12 | 2004-06-22 | 40 | 2004-05-15 | 2004-06-24 | 39 | -1 | 450 | 430 | -20
Contoso Pharmaceuticals | Process Reengineering | 2004-06-14 | 2004-08-12 | 58 | 2004-06-16 | 2004-08-16 | 60 | 2 | 230 | 235 | 5
TOTAL |  |  |  | 404 |  |  | 428 | 24 | 3730 | 3785 | 55