## Marketing Tactical Plan
Marketing Tactical Plan
Instructions: Use this template to track the marketing tactics you need to complete as you carry out your marketing strategy.
Status key: |  | On track
Minor glitches that need attention but will not delay the deliverable
Major glitches that need attention and will (or most likely will) delay the deliverable
Products requirements definition (Sample)
Task | Owner | Actual Expense | Mar | Apr | May | Jun | Jul | Aug | Status | Comments
Complete the products requirement definition document | Tom | 1500 | [7 empty] | COMPLETE. Task was in progress for two months and finished at the end of April. | bar: Mar to Apr
Review with product development team; gather feedback; incorporate feedback | Tom | 400 | [7 empty] | Tom has set up a meeting with the team next week. | bar: May
Give document to product development for prototype development | Michelle | 500 | [7 empty] | Michelle on unexpected medical leave, so we need to work around her absence. We will be able to complete this task, but we need to make sure that the schedule doesn't slip. | bar: May
Total Expense: | 2400
Total Elapse Time: | 3 | Months
Dependencies on: | Marketing strategy
Dependencies for: | Pricing, Marketing communications activities
General comments: | Initial feedback from product development team was very positive—things are looking good!
<Key Marketing Deliverable>
Task | Owner | Expense | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Status | Comments
0
0
0
0
0
0
0
0
0
0
0
Total Expense: | 0
Total Elapse Time: |  | Months
Dependencies on: | <Enter key marketing deliverables that provide input to this marketing deliverable.>
Dependencies for: | <Enter key marketing deliverables that receive or are dependent on input from this marketing deliverable.>
General comments:
<Key Marketing Deliverable>
Task | Owner | Expense | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Status | Comments
0
0
0
0
0
0
0
0
0
0
0
Total Expense: | 0
Total Elapse Time: |  | Months
Dependencies on: | <Enter key marketing deliverables that provide input to this marketing deliverable.>
Dependencies for: | <Enter key marketing deliverables that receive or are dependent on input from this marketing deliverable.>
General comments:
[Key Marketing Deliverable]
Task | Owner | Expense | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Status | Comments
0
0
0
0
0
0
0
0
0
0
0
Total Expense: | 0
Total Elapse Time: |  | Months
Dependencies on: | <Enter key marketing deliverables that provide input to this marketing deliverable.>
Dependencies for: | <Enter key marketing deliverables that receive or are dependent on input from this marketing deliverable>
General comments:
[Key Marketing Deliverable]
Task | Owner | Expense | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Status | Comments
0
0
0
0
0
0
0
0
0
0
0
Total Expense: | 0
Total Elapse Time: |  | Months
Dependencies on: | [enter key marketing deliverables that provide input to this marketing deliverable]
Dependencies for: | [enter key marketing deliverables that receive or are dependent on input from this marketing deliverable]
General comments:
[Key Marketing Deliverable]
Task | Owner | Expense | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Status | Comments
0
0
0
0
0
0
0
0
0
0
0
Total Expense: | 0
Total Elapse Time: |  | Months
Dependencies on: | [enter key marketing deliverables that provide input to this marketing deliverable]
Dependencies for: | [enter key marketing deliverables that receive or are dependent on input from this marketing deliverable]
General comments: